## Project Trouble shooting
Project Issues & Root Cause Analysis (RCA) Register
Issue ID | Configuration Area | Business Process | User/ System Issue | Root Cause | Resolution | Validation Status
SD-001 | Customer & Material Master | Sales Order | Sales Area is not defined while creating Sales Order | Customer or Material was not extended to the required Sales Area | Verified Customer in XD02 and Material Sales Area; maintained the correct Sales Area (MNX1/4J/HJ) | Resolved
SD-002 | Pricing | Sales Order | Price displayed 0.00 in Condition tab | Pricing Procedure Determination was incorrect | Verified Condition Type, Pricing Procedure, then corrected OVKK determination | Resolved
SD-003 | Shipping Point Determination | Sales Order | Shipping Point was determined as a different value instead of FXL9 | Shipping Point Determination configuration was incomplete | Maintained the correct Plant, Shipping Condition, Loading Group & Shipping Point in OVL2 | Resolved
SD-004 | Storage Location Determination | Delivery | Storage Location was not fetched automatically during Delivery | Automatic Storage Location Determination was missing | Configured Shipping Point, Plant & Storage Location mapping in OVL3 | Resolved
SD-005 | Inventory / Batch Management | PGI | Deficit of SL Unrestricted-Use Stock during PGI | No unrestricted stock available for the batch-managed material | Updated stock through MIGO, verified inventory in MMBE, and used the correct Batch Number | Resolved
7 | Revenue Account | Billing | Revenue G/L not posted | Revenue Account Determination incomplete | Assigned G/L 175000 with Account Determination Procedure and validated FI document | Resolved
SD-008 | Text Determination | O2C | Customer text not copied to Sales Order | Incorrect Text Procedure / Access Sequence mapping | Configured C1, C2, C3, C4 procedures and Access Sequences 26, 27, 28 | Resolved
SD-009 | Credit Management | Sales Order | Error: Input values must be defined in Table T691A | Custom Credit Control Area (JX01) and Risk Category (X01) not supported in demo server table | Identified demo server limitation and reverted to standard configuration | Resolved
SD-010 | Credit Management | Sales Order | Customer not found for Credit Control Area | Customer was not assigned to Credit Control Area | Extended Customer/BP with JX01 and maintained credit data in FD32 | Resolved
SD-012 | Pricing | Configuration | Unable to edit field in V/07 | Standard SAP object was display/protected | Created and maintained a custom Access Sequence instead of modifying standard | Resolved

## Configuration Sheet
SL | Area | Configuration | Value
1 | Company Code | Company Code | 1000
2 | Enterprise Structure | Sales Organization | MNX1
3 | Enterprise Structure | Distribution Channel | 4J
4 | Enterprise Structure | Division | HJ
5 | Enterprise Structure | Sales Office | AFS9
6 | Enterprise Structure | Sales Group | 4Q
7 | Enterprise Structure | Shipping Point | FXL9
8 | Master Data | BP Group | GMCS
9 | Master Data | Account Group | GSX9
10 | Pricing | Condition Type | XRK0
11 | Pricing | Pricing Procedure | RVNN01
12 | Pricing | Condition Table | 547
13 | Pricing | Access Sequence | ASD9
14 | Revenue | Account Determination | KL07
15 | Revenue | G/L Account | 175000